## Status Report
Project Name | HomeChef |  | Date |  | 2024-02-03 | Project Manager |  | Austin Clarke
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
This android app will enable users to upload their groceries to the app using their receipt. The groceries will be visible on the app through their virtual pantry. The main goal of the app is to recommend recipes based on groceries that the user already owns. |  |  |  | Assign team roles |  | 100% | Complete
|  |  |  | Create the login screens |  | 100% | Complete
|  |  |  | Create the register screens |  | 0% | Future Task
|  |  |  | Research user authentication methods |  | 0% | Future Task
|  |  |  | Research UPC data for database storage |  | 0% | Future Task
|  |  |  | Design database objects |  | 45% | Possible Delays
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Roles have been assigned to each team member with tasks assigned according to roles. | [5 empty] | Emily will be working on the register view before the next meeting. Austin will be looking into UPC data to determine the presentation of the virtual pantry. Amy will be looking at whether or not we will use aws cognito for user authentication. Nat continue with grocery item design as soon as Austin is done with research.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Clarke | Project Manager | 4 | Risk | Slow performance of recipe search. Lack of recipes in the database.
Nat Poulson | Chief Architect | 3.5
Emily Asplund | Frontend Architect | 5
Seth Fredrickson | Backend Architect | 4.5 | Issue | Uncertain how ingredients will be categorized and displayed. Unknown how recipes will be queried based on the ingredients.
Amy Techavimol | API Designer | 3.5
Rachel Perrier | Quality Assurance | 3
Total |  | 23.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task